## LESSONS LEARNED
LESSONS LEARNED
PROJECT NAME | Data Science Live Project
PROJECT ID
PROJECT MANAGER | JAYANTH G.S
PROJECT SPONSOR | Cloud Counselage
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2020-07-10 | Model Overfitting the Data | Technical | None | Cross-Validate the score | Performed 20-fold cross-validation | Krunal Doshi | Closed
2 | 2020-07-15 | Merging different Plots | Technical | None | Using Supported Libraries from Matplotlib | Changed the libraries and format | Krunal Doshi | Closed
3 | 2020-07-17 | Different outputs from Jupyter and cmd | Technical | None | Use methods that give proper output from cmd | Standardized the output | Krunal Doshi | Closed | Closed plots and cleared axes after saving to pdf