## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Data Science Live Project
PROJECT SPONSOR | Cloud Counselage Pvt. Ltd.
PROJECT MANAGER | Jayanth G S
EXPECTED START DATE | 15/06/2020
EXPECTED COMPLETION DATE | 31/07/2020
ESTIMATED COST | 0
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | Visualization of dataset and identification of the best classifier for the dataset
BUSINESS CASE | This project adds value to the Internship Program through analysis of data acquired from it. It will enable the company to better understand how to judge the eligibility of an individual from the metrics available, identify the technologies students are interested in and identify the platforms that reach more students. This project is essential to reap the benefits of the Internship Program.
GOALS/METRICS | Good Classification Accuracy and an understanding of the data acquire from Internship Program
EXPECTED DELIVERABLES | Visualizations that represent the dataset and a classifier that accurately classifies the data
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | Static Visualizations representing the dataset exported as pdf, the best classifier's name and the accuracy in console output
OUTSIDE OF SCOPE | Html output with interactive dashboard and the best classifier with several metrics like f1 score, precision, recall, roc, auc, accuracy, etc
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Krunal Doshi wil be working with Python
SUPPORT RESOURCES | matplotlib, seaborn, scikit-learn, pandas, numpy and other python packages
SPECIAL NEEDS | None
PROJECT BENEFITS AND CUSTOMERS
PROCESS OWNER | Krunal Doshi
KEY STAKEHOLDERS | Jayanth G S
END CUSTOMER | Cloud Counselage Pvt. Ltd.
EXPECTED BENEFIT | This project will enable the company to better understand how to judge the eligibility of an individual from the metrics available, identify the technologies students are interested in and identify the platforms that reach more students.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | Corruption of the .py file
ASSUMPTIONS | Data acquired is correct and reliable, client has the necessary configuration required to run the code and view exported files
CONSTRAINTS | Entire code should be written in python