## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Project title: | Data Science Live Project |  | Project Id: |  | Project Manager: | JAYANTH G S |  |  | Assumption | 2 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | Issue | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | v |  | Project Team Lead: | Krunal Doshi |  |  | Dependency | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 5 |  |  |  |  | #VALUE!
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Technologies having a space at the end as "DATA SCIENCE " not noticed | Visualiazation wont happen and it will keep giving errors | Print all the technology words in the list so as you get to know exact usage | Krunal Doshi | Critical | 100 | Closed | Risk
2 | Assumption | Data is authentic | we can work without any doubt | Check with the source | CLOUD COUNSELAGE | High |  | Closed | Assumption
3 | Risk | Classifier overfits or dataset is too small for classifier | Reliability of obtained metrics will be compromised | Research well and select the ideal classifier | Krunal Doshi | Critical | 30 | Closed | Issue
| Risk | Preprocessing isn't carried out properly | noisy dataset | Look at the dataset properly and understand it well so that its cleaned properly | Krunal Doshi | Moderate | 70 | Closed
5 | Assumption | Reliability of results | Significant differences in result as test data is changed | Train and tune model properly | Krunal Doshi | High |  | Closed
6 | [8 empty] | Open
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24